## Tasks
Item | Time Required | Comments | Status
Review temp area | Completed |  | Done
Review embedded layout | Completed |  | Done
Virtual overs disappear when form is closed | Completed |  | Fixed
Completion on of rotated shapes | Completed |  | Done
Review how overs generator work | Completed |  | Done
Make counters active when selected | Completed |  | Done
Put in trap for gross < net and selected = 100% | Completed | Fixed related bug | Done
In seams mode, when only one finish is showing, select it | 1 Hour
Tool tips on 'flips' on combos | 2 Hours
Change B key to X key to show cross hairs | 1 Hour
Fix bug where you can't select embedded areas | 1 Day
Implement drawing circles | 2 Days
Rug pattern matching | Don't know
Add ability to put in text boxes | 1 Day
Add ability to add text to counters | 4 Hours
Rotate background image and shapes | 2 Weeks
Allow take outs to cross boundaries | 3 Weeks | Involves backing in new geometry engine
When line is chosen, undo zero line | 1 Hour
Edit shape allow breaking of lines | 3 day
Change size of hash marks in legend | 2 days
Fix Message Box Adv | 1 Day

## Sheet1
Diagram Libraries | Replacement for Visio COM Add In
Syncfusion Diagram
MidFusion Diagramming for WinForms/WPF/ASP.Net
GoDiagram By Northwoods Software
DevExpress Diagram Control
yFiles for .Net
Nevron Diagram for .Net
QuickGraph
Draw2D.Net
Diagram.Net